# OE3C CCOVI Planning Meeting Agenda

Monday, February 23, 2026 (11 AM to 12 PM), MS Teams

Attendees: Taylor MaGee (CCOVI/CWL) Madelaine Legault (OE3C)

Absent: Alex Wilder, Nicholas Benton, Wylan Clitheroe (OE3C)

| Time | Agenda Item | Lead |
| --- | --- | --- |
| 11:00-11:10 | Introductions, objectives | Madelaine |
| 11:10-11:30 | CCOVI Tours - Scheduling (when, where) - CCOVI suggests one tour with tasting incorporated – 1.5 hours total - Selected event date: April 30th 3-4:30 - Where should folks meet? Wine Library (LOC member to bring folks to location) - Attendance limits, registration - 20 max (comfortable), 25 can be tight - We would request sign-ups at registration so that we have an ideas of #s - Pricing of wine, notice for ordering - Cost breakdown from Taylor: 4-6 bottles, around $15-20 per person; ordered once we have #s; 2 weeks' notice would be ideal, stragglers to be added up to 1 week before event - EDIT 03/05: registration cost for participants $10, we will budget the rest - Recommended wines? Taylor can recommend closer to date with numbers, will select for us - Out of general cellar not necessarily the CWL, though Taylor will look into incorporating one of this collection for tasting feedback (TBD) - Additional requirements from CCOVI? - No need to ID, just keep an eye out on registration for ages; make a note in registration that it is a 19+ even (Taylor would ID if anyone looked under 19). - Someone from LOC to tag along and help out with tour (e.g., bring attendees to tour location, open doors, etc.) | Madelaine |
| 11:50-12:00 | Summary, overview of action items and timelines - Send calendar invite to Taylor to hold date (ML) - Inform Taylor of attendee #s by April 16th (ML) | Madelaine |