OE3C Outings/Workshops Sub-Committee Meeting Notes
January 12th, 2026, 10:30 AM – 11:30 AM (MS Teams)

Attendees: Nicholas Benton [NB], Madelaine Legault [ML], Wylan Clitheroe [WC]

Notes: ML, transcript recorded and saved

- Hikes

NB: Schedule (time on first day for workshops/outings, morning hike)

WC: morning hike, rewilding, Glenridge Quarry, bioblitz in second hour (using iNaturalist)

NB: we should let Quarry know that we’re doing hike there, has contact, will send email with details about hike and bioblitz

WC: will get details sorted soon so NB can send off to contact

WC: night hike/salamanders would be cool ideas but would require some additional planning (transportation, timing, etc.), would need to be sorted closer to.

NB: might be done by conference time, probably not worth it to go to NC; Escarpment might have some salamanders (herpetology night?)

WC: evening or nighttime hikes would require safety PPE (head lamps—rental?); scrapping nighttime hike would likely be the route we take

NB: let’s focus on morning hike on first day

ML: would morning hike be well-attended on first day? Ppl coming in on public transport may not have place for their belongings or even be arriving that early? Last day morning hike?

NB: if bad weather, no rain check option

WC: could plan an alternate option

NB: could see collections

ML: incorporate scavenger hunt as backup, would require relatively few resources

NB: could do both, start at ecology room with samples with some part of scavenger hunt, then ppl could go out and explore MacChown (can return to ecology room as end point)

WC: will create doc to start planning

ML: could have both at same time, cancel hike if inclement weather; accessible option

WC: less people on hike would be okay, more personalized conversations

WC: planning needs: first aid kit, multiple people as organizers/volunteers on hike

NB: how many? Say if 50 participants

WC: maybe 1-2 additional people

NB: doable, scavenger hunt could have one person; would have to talk to Alex about reworking schedule

- Workshops

- CCOVI

  - Initiate planning, contact Taylor and Steve (with Alex?)

  - When – Thursday before social? YES

  - ML: work with Alex on contacting and go from there

- Coding

  - Workshop facilitator? Topic? When?

  - NB: could do GIS, will talk to Rasa about ideas and go from there in next two weeks; on first day (second smaller segment on schedule)

- Indigenous ecology topic

  - Reach out to Cindy at Hadiya’dagendahs to discuss topics and workshop facilitators; When?

  - WC: after keynote on second day

  - ML: will go to PowWow and purchase medicines for gifting; maybe we can aim to contact by end of January

- Photography workshop from Dr. Gotanda

  - Do we want to include this?

  - WC: Kyoko has it done, needs to know when; good for first day

- Photo competition

- Hosting platforms, costs (budget requests), setup

- Themes/categories, parameters

- Prizes (start reaching out for donations?)

  - Local products/goods and services (e.g., RPM Bakehouse gift certificates, Niagara fruit jams/sauces/provisions/wine baskets, Brock/OE3C swag)

- Coordinate with Matt to advertise on social media

- ML: let’s all read and add thoughts to planning doc, discuss hosting platforms and categories, prizes

- WC: prizes – books, field guidebooks

- NB: gift certificates may not be great for folks travelling in from far away

- Outings

- WC: Second day evening? Trip to NF

- NB: outing during one of the workshops?

- WC: First day afternoon?

- NB: during photography workshop? Hotel check-in at 2:30

- ML: let’s brainstorm second outing ideas

- WC: short hike with mindfulness activity, onsite? Will edit schedule to reflect today’s meeting

- Silent art auction

  - Draft call for submissions

  - Coordinate with Matt to advertise on social media

  - Materials, logistics

- ML: biting off more than we can chew? Scrap

- WC: could just do an art gallery for viewing? Could work with Brock for submissions

- ML: could include purchasing info if possible, commissioning option

- WC: self-directed activity; can reach out to artists/Brock, share poster

- Passes

- Start reaching out to acquire (NF, Clifton Hill, downtown STC, NOTL, Jordan)

- ML: revisit this later

- In-between/downtime self-directed activities

- Float some ideas on making a local guide / little activity list for people to do if they have down time (ex. MacChown display scavenger hunt, specimen display for people to look at, local eats/downtown activities)

- See “Hikes” for meeting notes.

ACTION ITEMS:

WC: schedule, hike, outline for scavenger hunt

NB: photo competition, Kyoko for photog, Rasa for Coding

ML: discuss with Alex for CCOVI and Indigenous ecology workshops