OE3C Local Organizing Committee – Planning meeting 1

Date: October 27, 2025

Time: 10:00AM - 11:30AM

Location: Microsoft Teams meeting (virtual)

Chair: Kiyoko Gotanda & Alex Wilder

Minutes: Lyllian Corbin

| Time | Topic | Discussion Lead |
| --- | --- | --- |
| 5 min | Round table introductions | Kiyoko |
| 10 min | House keeping - Dates - Theme - Record keeping - Secretary: Lylly - Any email should cc oe3cofficial@gmail.com - Code of conduct - Undergrad rep applications - Shortlist 6 if necessary, based off preliminary scoring and will provide to LOC with score sheet after deadline | Kiyoko and Alex |
| 5 min | Trello & Teams - Trello - See link to join Trello in Teams channel - Use Trello to manage tasks and indicate what you are working on - Items to be covered in the next meeting should be added to the board 48 hours before meeting to be included in agenda. - Teams - Channels are for posts and discussions between subcommittee members - Please keep all documents in the files and docs channel and post links in respective channels to link them | Alex |
| 10 min | Accommodations - Four points - 50 rooms at $160 - Can add more once they fill - IHG Group hotels - Waiting for contract - Holiday Inn, Best Western, Stay Inn, Hampton - Questions/ Comments | Alex |
| 15 min | Subcommittees and leads - Advertising, Coms, and promotions - Lead: - Webmaster: Rasa Khosrowshahli - Social media manager: Matthew Summerville - Fundraising and finance - Lead: Alex Wilder - Budget lead: Sarah Hein - Outings and Socials - Lead: Madelaine Legault (assist) - Abstracts, schedules, and programs - Lead: Nick Benton - Registration Lead: Reem Mahamoud - Workshops, Speakers, Seminars - Lead: Nick - Keynote Lead: - Bookings and records - Lead: Lylly | Alex |
| 5 min | Logos - Lauren working on logo - Comms materials as soon as this is done | Alex & Lauren |
| 10 min | Timeline - 50% Hotel rooms released: March 10th - 100% Hotel room released: March 29th - Tentative abstract/presenter registration deadline: March 10th - Abstract/ presenter registration closes: March 29th - Attendee registration closes: | Alex |
| 10 min | Keynote Speakers - Need one speaker for each E - See list in teams for ideas - Keynote lead to research and choose top choices for each E - Report back next meeting | Alex |
| 10 min | Workshops Outings Socials - Please see the teams files and documents channel for the respective docs and add your ideas before Oct 31st for the Nov 3rd meeting | Alex |
| 10 min | Questions and General Discussion | All |